## Sheet1
2018-2022 Short Term Work Plan - Report of Accomplishments
# | Project | Completed | Underway | Postponed | Dropped | Notes
ECONOMIC DEVELOPMENT
ED1 | Host annual downtown business open house; Host annual reception for downtown property owners. |  |  | x |  | Evaluating an alternative in light of COVID or will postpone until we are beyond the pandemic
ED2 | Recruit sustainable development on Lewis Road |  | x
ED3 | Market development of South Square |  | x
ED4 | Market redevelopment areas |  | x
ED5 | Public outreach: messenger; signage; brochures and cards, and website review to be conducted bi-monthly |  | x
ED6 | Issue RFP for design/engineering of the Powder Springs town center and redevelopment area | x
ED7 | Master plan to define south square |  | X
ED8 | Develop Economic Development Strategy – update annually, including evaluation of marketing to hits on city and economic development websites |  | x
ED9 | Host annual meetings with local businesses, including those within industries recommended for recruitment in Fanning Report |  |  | x |  | Postpone IN PERSON to post COVID.
ED10 | Identify and attend industry events occurring within the region |  |  | x |  | Postponed due to COVID. Contracted with NextSite to attend retail events on behalf of the City.
ED11 | Inventory and assess all potential and existing industrial and commercial properties |  | x
ED12 | Create printed and electronic site information packets on potential developmentareas, vacant sites, and downtown properties. Create brochures for targeted industries. |  | x
ED13 | Recruit developer for mixed use remodel of existing town square |  | x
ED14 | Examine areas for potential industrial use |  | x
ED15 | Continue strengthening capacity of DAPS and DDA |  | x
ED16 | Expand relationships with Cobb County and external partners |  | x
ED17 | Continue expanding relationships with Cobb County and external partners |  | x
ED18 | Continue to develop incentives policy program |  | x
ED19 | Market the economic development office as THE “go-to” for local business owners in solving problems |  | x
ED20 | Continue to widely publicize the programs and services available through the Powder Springs Economic Development Department |  | x
ED21 | Further develop the local business ambassador program |  |  | x |  | Started business surveys program, but did not complete due to Covid.
ED22 | Continue intentional, one-on-one outreach to local businesses |  | x
ED23 | Develop an online directory of businesses | x
ED24 | Continue to update online directory of businesses |  | x
ED25 | Host business tours for community leaders |  |  | x |  | Postponed due to COVID. DAPS discussed hosting driving tours prior to the pandemic interruption.
ED26 | Explore the potential to develop a mobile application to feature local businesses |  |  |  | x | This project has been removed.
ED27 | Continue helping local businesses engage with local schools |  | x
ED28 | Continue to convene downtown business and property owners together on a regular basis |  |  | x |  | COVID impacts; this year we offered outdoor coffee and donuts
ED29 | Host a tour of available properties with regional developers |  |  | x |  | Planning underway but impacted by COVID.
ED30 | Host a Developers Day |  |  | x |  | Planning underway but impacted by COVID.
ED31 | Create an internship program |  |  | x |  | Limited resources
ED32 | Create a video on "Why Powder Springs?" |  |  | x
ED33 | Explore resources available through Kennesaw State University |  | x
ED34 | Convene real estate brokers and property owners for commercial and industrial properties |  |  | X
ED35 | Gather intelligence on “market holes” in Powder Springs |  | x
ED36 | Assist with the restart of the Powder Springs Business Association | x
ED37 | Explore the feasibility of developing a co-working space |  |  | x
ED38 | Develop a tutorial on how to do business in Powder Springs |  | x
ED39 | Develop a small business resource guide | x
ED40 | Investigate potential for development of a TAD with county and school support |  |  |  | X | Limited resources
ED41 | Investigate the potential for a National Main Street and Georgia Main Street Designation |  | x
ED42 | Conduct a marketing and branding study that will research Powder Springs' target demographic(s), and create strategies for attracting new residents, business owners, toursists, and development. |  | x
ED43 | Recruit a catalytic business for the downtown |  | x
LAND USE
LU1 | Annex parcels identified in the comprehensive plan |  | x
LU2 | Update City boundary map with actions through the General Assembly--annual submittals as appropriates | x | x |  |  | Ongoing project
LU3 | Town Square Development: land acquisition and development of multi-use trail, amphitheater lawn, stage, play art, fountain, shared space with pavers, bocce | x
LU4 | Former Town Square landscape improvements, upgraded fountain, hardscaping | x
LU5 | Update the Unifed Development Code to eliminate disrepancies, make it more user friendly, and review and revise regulations |  | x
LU6 | Minor comprehensive plan update |  | X
COMMUNITY FACILITIES & SERVICES
C1 | Community Rating System to lower flood insurance premiums | x |  |  |  | Ongoing
C2 | Facilitate functions and events on square |  | x | x |  | Ongoing where we can (M2R art; trunk or treat drive through) but postponed large events
C3 | Develop an RFP for planning services for a Greenspace master plan |  |  | X |  | This task was updated to be "Continue to protect greespae and continue to implement park plans"
C4 | Construct parking garage downtown |  |  | X
C5 | Implement sidewalk improvements based upon study recommendations | x
C6 | Prepare appropriate redevelopment plan based on LCI study |  | x
C7 | Infrastructure reporting implementation |  | x
C8 | Lancer Sidewalks Phase II |  |  | x |  | Programmed for 2023
C9 | Theatre and reception hall: market for events, schedule events, and maintenance | x
C10 | Citizen survey |  | x
C11 | Develop marketing and use strategy for city trails (5K; PD Bike Patrol; Cameras; etc.) |  | x | x
C12 | Develop road rating system to serve as basis for road improvement projects and update every 3-5 years | x
C13 | Institute Community Policing Program to include CAP, Bridge Gap meetings, Business Watch, etc |  | x
C14 | Institute Community Emergency Response Team program; update COOP |  | x
C15 | Develop capital improvement plan for facilities, equipment, and infrastructure |  |  | x |  | Programmed for 2022
C16 | Evaulate information technology back up resources and services | x
C17 | Implement E-billing option for residents to receive their monthly water bill |  |  |  | x | Water system sold to county
C18 | Expanded recreational facility: multi-use trails, 3 multi-purpose fields, 4 tennis courts, parking, restroom facility, landscaping |  |  |  | x | Removed – Not a current funded or prioritized project.
NATURAL & HISTORIC RESOURCES
NH1 | Seven Springs Walking Tour Markers; update and implement trail signage program. |  | x
NH2 | Phase II of park | x |  | x
NH3 | Continue phase IV of linear park |  | x |  |  | Master plan completed; funding restricts implementation of all features. Special needs playground installed; basketball court installed. As impact fees are collected additional features to be added. Changed to read "Linear Park"
NH4 | Impact fee program update for linear park | x
NH5 | Maintenance of Landscaping on parkway/roads & at newly landscaped areas |  | x
NH6 | Develop tourism strategy centered around recreation and entertainment to include Bodiford House |  |  |  | x | Removed – Not a current funded or prioritized project.
NH7 | Investigate the potential for designating a local historic district and forming a historic preservation commission |  |  |  | x | Removed – Not a current funded or prioritized project.
NH8 | Conduct a signage and wayfinding study that builds off the branding study from ED42 and creates a strategy to increase awareness of Powder Springs for Silver Comet Trail users, increase wayfinding capabilities throughout the City's trail system, and create cohesive and attractive signage throughout the City. |  | x
NR4 | Continue to increase awareness to the downtown district from the Silver Comet Trail, city trails and gateways with increased signage or other opportunities. |  | x |  |  |  | NEW
NR5 | Bike Friendly Certification |  | x |  |  |  | NEW
NH9 | Implement the recommendations of the signage and wayfinding study |  | x |  |  |  | NEW
TRANSPORTATION
ADDITIONAL STUDIES
T1 | C H James Parkway & Brownsville Road |  |  | x |  | Programmed 2023
T2 | C H James Parkway & Hill Road |  |  | x |  | Programmed 2023
T3 | Richard D Sailors Parkway & Old Lost Mountain Road |  |  | x |  | Programmed 2023
T4 | Brownsville Road & Hiram-Lithia Springs Road |  |  | x |  | Programmed 2023
T5 | Powder Springs Road @ Richard D Sailors Parkway / Powder Springs Rd |  |  | x |  | Programmed 2023
T6 | Corridor study for Powder Springs Road | x
T7 | Corridor study for Austell Powder Springs Road | x
ROADWAY
T8 | Murray Avenue A (Hotel Avenue to Atlanta Street): Remains one way, add 20’ angled parking on both sides |  |  |  | x
T9 | Murray Avenue B (Atlanta Street to Lewis Road): Add 18’, 90 degree parking on one side |  |  |  | x
T10 | Butner Street Extension: Add 20’ angled parking each side, add two 10’ travel lanes |  |  | x |  | Programmed 2023
T11 | Jackson Way Reconfiguration: two 10’ travel lanes |  |  |  | x
T12 | Hotel Avenue Extension: Add 20’ angled parking on both sides, add two 10’ travel lanes |  |  |  | x
T13 | Florence Road @ C H James Parkway |  |  | x |  | Programmed 2023
T14 | Brownsville Road @ Oglesby Road |  |  | x |  | Programmed 2023
T15 | New Macland Road @ Publix and Home Depot |  |  | x |  | Programmed 2023
T16 | Brownsville Road @ Kroger |  |  | x
T17 | Widen New Macland Road |  |  |  | x | Removed – Not a current funded or prioritized project.
T18 | C H James striping and pavement marker improvements |  |  | x |  | Programmed 2023
T19 | Curb cut off C.H. James Parkway with access road to Oglesby Road with new traffic signals |  |  | x |  | Programmed 2023
T20 | Curb cut off C.H. James Parkway near Hill Road |  |  | x |  | Programmed 2023
T21 | Realignment of Flint Road at Powder Springs Road | x
T22 | Curb cut off C.H. James Parkway near Florence Road with access road |  |  | x
T23 | Curb cut off C.H. James Parkway at Paulding County line, with access road connecting to Sterlingbrooke Drive and traffic light |  |  | x
T24 | New traffic signal at C.H. James Parkway at Sweetwater Avenue |  |  | x
T25 | New traffic signal at C.H. James Parkway at Sterlingbrooke Drive |  |  | x
BICYCLE/PEDESTRIAN
T26a | 10' Concrete Multi-Use Trail Alternative A: Retrofit sidewalk on Lynn Drive from Old Lost Mountain Road to parking lot off Jackson Way to connect Silver Comet Trail Connector on Old Lost Mountain Road to the parking lot off Jackson Way |  |  | X |  | Funding
T26b | 10' Concrete Multi-Use Trail Alternative B: From Silver Comet Trail Connector along Old Lost Mountain Road to Oakview Drive to Downtown/Lewis Road |  |  | x |  | Funding
T27 | Recreation Trails: 12’ asphalt trail from Brownsville Road south through floodplain |  |  | x |  | Funding
T28 | Designate a Trail Head at at the intersection of Oakview Drive and Jackson Street at existing parking lot | x |  |  |  | Trailhead developed as part of park project. This item can be removed.
T29 | Austell Powder Springs Road Pedestrian Improvements |  |  | x |  | Funding
T30 | New Macland Road Pedestrian Improvements |  |  | x |  | Funding
T31 | Macedonia Road Pedestrian Improvements |  |  | x |  | Funding
T32 | Powder Springs Dallas Road Pedestrian Improvements |  |  | x |  | Funding
T33 | Hill Road Pedestrian Improvements |  |  | x |  | Funding
T34 | Carter Road Pedestrian Improvements |  |  | x |  | Funding
T35 | Elliott Road Pedestrian Improvements |  |  | x |  | Funding
T36 | Powder Springs Creek Trail |  |  | x |  | Funding
T37 | Lewis Road Landscape: median landscaping along whole corridor, inside median and at back of sidewalk |  |  | x |  | Funding
T38 | Butner Street Streetscape: landscaped planters, sidewalks |  |  | x |  | Funding
T39 | Jackson Way Streetscape: reconfiguration, landscaped planters, sidewalks, both sides |  |  | x |  | Funding
T40 | Hotel Avenue Streetscape: landscaping, sidewalks from Murray Avenue to Butner Street |  |  | x |  | Funding
T41 | Dillard Street Sharrow Markings: from Pineview Drive south to Atlanta Street |  |  | x |  | Funding
T42 | Atlanta Street Sharrow Markings: from Dillard Street to Old Austell Road |  |  | x |  | Funding
T43 | Marietta Street Sharrow Markings: from Dillard Street to Old Lost Mountain Road and Powder Springs Dallas Road intersection |  |  | x |  | Funding
T44 | Powder Springs/Dallas Road Sharrow Markings: from Old Lost Mountain Road to Lucille Creek Trail entrance |  |  | x |  | Funding
T45 | Grady Grier Drive Sharrow Markings: to Old Austell Road |  |  | x |  | Funding
T46 | Hopkins Road Sharrows |  |  | x |  | Funding
T47 | Brownsville Road Sharrows |  |  | x |  | Funding
TRANSIT
T48 | MARTA connection bus |  |  | x |  | Funding
T49 | Flex Bus expansion |  |  | x |  | Working with Cobb DOT

## Sheet2
T42 | Curb cut off C.H. James Parkway with access road to Oglesby Road with new traffic signals | x | x |  |  |  | Public Works | TBD | TBD
T43 | Curb cut off C.H. James Parkway near Hill Road |  | x | x |  |  | Public Works | TBD | TBD
T44 | Realignment of Flint Road at Powder Springs Road |  |  |  |  | x | Public Works | TBD | TBD | 550000 in Cobb 2016 SPLOST
T45 | Curb cut off C.H. James Parkway near Florence Road with access road |  |  | x | x |  | Public Works | TBD | TBD
T46 | Curb cut off C.H. James Parkway at Paulding County line, with access road connecting to Sterlingbrooke Drive and traffic light |  |  |  |  | x | Public Works | TBD | TBD
T47 | New traffic signal at C.H. James Parkway at Sweetwater Avenue |  | x |  |  |  | Public Works | TBD | TBD
T48 | New traffic signal at C.H. James Parkway at Sterlingbrooke Drive |  |  |  |  | x | Public Works | TBD | TBD
T6 | Corridor study for Powder Springs Road | [5 empty] | Public Works
T7 | Corridor study for Austell Powder Springs Road | [5 empty] | Public Works