## Sheet1
City of Powder Springs Short Term Work Plan (2018-2022)
# | Project | 2018 | 2019 | 2020 | 2021 | 2022 | Responsible Party | Estimated Cost | Funding Source | Notes
ECONOMIC DEVELOPMENT
ED1 | Host annual downtown business open house; Host annual reception for downtown property owners. | x | x | x | x | x | Economic Development | TBD | TBD | Part of the City's 2016-2020 STWP
ED2 | Recruit sustainable development on Lewis Road and near U.S. 278 | x | x | x | x | x | Economic Development | TBD | TBD | Part of the City’s 2016-2020 STWP
ED3 | Market development of South Square | x | x | x | x | x | City Manager; Economic Development; DAPS; DDA | Staff | - | Part of the City’s 2016-2020 STWP
ED4 | Market redevelopment areas | x | x | x | x | x | City Manager; Economic Development; DAPS; DDA | Staff | - | Part of the City’s 2016-2020 STWP
ED5 | Public outreach: messenger; signage; brochures and cards, and website review to be conducted bi-monthly | x | x | x | x | x | City Manager; Economic Development; DAPS; DDA | Staff | - | Part of the City’s 2016-2020 STWP
ED6 | Issue RFP for design/engineering of the Powder Springs town center and redevelopment area | x |  |  |  |  | City Manager; Economic Development; City Clerk | 25000 | General fund | Part of the City’s 2016-2020 STWP
ED7 | Develop and continue to refine South Square redevelopment area | x |  |  |  |  | Community Development; SPLOST Program Manager; Economic Development | 26500 | General fund | Part of the City’s 2016-2020 STWP
ED8 | Develop Economic Development Strategy – update annually, including evaluation of marketing to hits on city and economic development websites | x | x | x | x | x | Community Development; Economic Development | 30000 | General fund | Part of the City’s 2016-2020 STWP
ED9 | Host annual meetings with local businesses, including those within industries recommended for recruitment in Fanning Report | x | x | x | x | x | City Manager; Economic Development; DAPS; DDA | TBD | General fund | Part of the City’s 2016-2020 STWP
ED10 | Identify and attend industry events occurring within the region | x | x | x | x | x | City Manager; Economic Development; DAPS | Staff | - | Part of the City’s 2016-2020 STWP
ED11 | Inventory and assess all potential and existing industrial and commercial properties | x | x | x | x | x | City Manager; Economic Development; DAPS | Staff | - | Part of the City’s 2016-2020 STWP
ED12 | Create printed and electronic site information packets on potential development areas, vacant sites, and downtown properties. Create brochures for targeted industries. | x | x | x | x | x | Economic Development | TBD | TBD | Part of the City’s 2016-2020 STWP
ED13 | Recruit developer for mixed use remodel of existing town square | x |  |  |  |  | Economic Development; DDA | TBD | TBD | Part of the City’s 2016-2020 STWP
ED14 | Examine areas for potential industrial use | x | x |  |  |  | Economic Development; DAPS; Consultant | TBD | TBD | Part of the City’s 2016-2020 STWP
ED15 | Continue training and strengthening capacity of DAPS and DDA | x | x | x | x | x | Economic Development; DAPS; DDA | Staff | - | Part of the City’s 2016-2020 STWP
ED16 | Continue expanding relationships with Cobb County and external partners | x | x | x | x | x | Economic Development | Staff | - | Part of the City’s 2016-2020 STWP
ED17 | Continue to refine and update incentives policy program | x | x |  |  |  | Economic Development | Staff | - | Part of the City’s 2016-2020 STWP
ED18 | Market the economic development office as the “go-to” for local business owners in solving problems | x | x | x | x |  | Economic Development | Staff | - | Part of the City’s 2016-2020 STWP
ED19 | Continue to widely publicize the programs and services available through the Powder Springs Economic Development Department | x | x | x | x | x | Economic Development | Staff | - | Part of the City’s 2016-2020 STWP
ED20 | Further develop the local business ambassador program | x | x | x | x | x | Economic Development | Staff | - | Part of the City’s 2016-2020 STWP
ED21 | Continue intentional, one-on-one outreach to local businesses | x | x | x | x | x | Economic Development; Community Development | Staff | - | Part of the City’s 2016-2020 STWP
ED22 | Develop and update an online business directory in partnership with the Powder Springs Business Group. | x | x | x | x | x | Economic Development | TBD | General fund | Part of the City’s 2016-2020 STWP
ED23 | Host business tours for community leaders | x | x | x | x | x | Economic Development; Consultants | TBD | TBD | Part of the City’s 2016-2020 STWP
ED25 | Explore the potential to develop a mobile application to feature local businesses | x |  |  |  |  | Economic Development | Staff | - | Part of the City’s 2016-2020 STWP
ED26 | Continue helping local businesses engage with local schools | x | x | x | x | x | Economic Development | TBD | TBD | Part of the City’s 2016-2020 STWP
ED27 | Continue to convene downtown business and property owners together on a regular basis | x | x | x | x | x | Economic Development | TBD | TBD | Carried over from current STWP
ED28 | Host a tour of available properties with regional developers | x | x | x |  |  | Economic Development | TBD | TBD | Part of the City’s 2016-2020 STWP
ED29 | Host a Developers Day | x | x | x | x | x | Economic Development | TBD | TBD | Part of the City’s 2016-2020 STWP
ED30 | Create an internship program | x | x |  |  |  | Economic Development | Staff | - | Part of the City’s 2016-2020 STWP
ED31 | Create a video on “Why Powder Springs?” | x | x |  |  |  | Economic Development | TBD | TBD | Part of the City’s 2016-2020 STWP
ED32 | Explore resources available through Kennesaw State University | x | x |  |  |  | Economic Development | Staff | - | Part of the City’s 2016-2020 STWP
ED33 | Convene real estate brokers and property owners for commercial and industrial properties | x | x | x | x | x | Economic Development | Staff | - | Part of the City’s 2016-2020 STWP
ED34 | Support efforts/activities of the Powder Springs Business Group | x | x | x | x | x | Economic Development | Staff | - | Part of the City’s 2016-2020 STWP
ED35 | Gather intelligence on “market holes” in Powder Springs | x |  |  |  |  | Economic Development; Consultants | TBD | TBD | Part of the City’s 2016-2020 STWP
ED36 | Explore the feasibility of developing a co-working space | x | x | x |  |  | Economic Development; Consultants | TBD | TBD | Part of the City’s 2016-2020 STWP
ED37 | Develop a tutorial on how to do business in Powder Springs | x | x |  |  |  | Economic Development; Community Development | Staff | - | Part of the City’s 2016-2020 STWP
ED38 | Develop a small business resource guide | x | x |  |  |  | Economic Development; Community Development | Staff | - | Part of the City’s 2016-2020 STWP
ED39 | Investigate potential for development of a TAD with county and school support | x | x |  |  |  | Economic Development; Community Development | Staff | - | Carried over from 2016 LCI Study
ED40 | Investigate the potential for a National Main Street and Georgia Main Street Designation | x | x |  |  |  | Economic Development; Community Development | Staff | - | Carried over from 2016 LCI Study
ED41 | Conduct a marketing and branding study that will research Powder Springs’ target demographic(s), and create strategies for attracting new residents, business owners, toursists, and development. | x | x |  |  |  | Economic Development; Community Development | 40000 | General fund
ED42 | Recruit a catalytic business for the downtown | x | x |  |  |  | Economic Development; Community Development | Staff | -
LAND USE
LU1 | Annex parcels identified in the comprehensive plan | x | x | x | x | x | All Departments | Staff | -
LU2 | Update City boundary map with actions through the General Assembly--annual submittals as appropriates | x | x | x | x | x | Community Development | Staff | - | Part of the City’s 2016-2020 STWP
LU3 | Town Square Development: trail head, land acquisition and development of multi-use trail, amphitheater lawn, stage, play art, fountain, shared space with pavers, bocce | x | x | x |  |  | Community Development; DAPS; DDA | 5310000 | SPLOST; reserve fund; bonds | Carried over from 2016 LCI Study
LU4 | Continuously review the Unifed Development Code and prepare additional updates as needed to eliminate discrepancies, make it more user friendly, and review and revise regulations | x | x | x | x | x | Community Development | Staff | General fund
LU5 | Minor comprehensive plan update |  |  |  | x | x | City Manager; Community Development | Staff | - | To be completed 5 years after this plan’s adoption. Needs to include updated demographics and market study, a Report of Accomplishments for this STWP, and a new STWP to reflect all changes.
COMMUNITY FACILITIES & SERVICES
C1 | Community Rating System to lower flood insurance premiums | x | x | x | x | x | Administration; Community Development | 5000 | General fund | Part of the City’s 2016-2020 STWP
C2 | Facilitate functions and events on square | x | x | x | x | x | Community Development | 20000 | General fund | Part of the City’s 2016-2020 STWP
C3 | Develop an RFP for planning services for a greenspace master plan to identify locations for future parks, programming needs, current levels of service, and funding mechanisms to fund all identified improvements. | x |  |  |  |  | Community Development | TBD | TBD | Part of the City’s 2016-2020 STWP
C4 | Construct parking garage downtown |  |  |  | x | x | Community Development, Public Works, SPLOST Program Manager, Economic Development, DDA | 3600000 | SPLOST | Part of the City’s 2016-2020 STWP
C5 | Implement sidewalk improvements based upon study recommendations | x | x |  |  |  | Community Development; Public Works | TBD | TBD
C6 | Prepare appropriate redevelopment plan based on LCI study | x | x |  |  |  | Community Development; Economic Development; DDA | TBD | General fund | Part of the City’s 2016-2020 STWP
C7 | Infrastructure reporting implementation | x | x | x | x | x | Community Development; Public Works | TBD | General fund | Part of the City’s 2016-2020 STWP
C8 | Lancer Sidewalks Phase II | x | x |  |  |  | Public Works | TBD | General fund; SPLOST | Part of the City’s 2016-2020 STWP
C9 | Theatre and reception hall: market for events, schedule events, and maintenance | x | x | x | x | x | Ford Board of Directors; City Manager; Economic Development | TBD | TBD | Part of the City’s 2016-2020 STWP
C10 | Citizen survey | x | x | x | x | x | City Manager; City Clerk | Staff | - | Part of the City’s 2016-2020 STWP
C11 | Develop marketing and use strategy for city trails (5K; PD Bike Patrol; Cameras; etc.) | x | x | x | x | x | Community Development; Police Department; Economic Development; City Manager | 40000 | General fund | Part of the City’s 2016-2020 STWP
C12 | Develop road rating system to serve as basis for road improvement projects and update every 3-5 years |  |  | x |  |  | Public Works | 43000 | General fund | Part of the City’s 2016-2020 STWP
C13 | Institute Community Policing Program to include CAP, Bridge Gap meetings, Business Watch, etc | x | x | x | x | x | Police Department | Staff | - | Part of the City’s 2016-2020 STWP
C14 | Institute Community Emergency Response Team program; update COOP | x | x | x | x | x | Finance; Police Department; Public Works; City Manager | Staff | - | Part of the City’s 2016-2020 STWP
C15 | Develop capital improvement plan for facilities, equipment, and infrastructure | x |  |  |  |  | Finance; Police; Public Works; City Manager | Staff | - | Part of the City’s 2016-2020 STWP
C16 | Evaluate information technology back up resources and services | x |  |  |  |  | Information Technology | Staff | - | Part of the City’s 2016-2020 STWP
C17 | Implement E-billing option for residents to receive their monthly water bill | x |  |  |  |  | Utilities; Finance | TBD | Utility funds | Part of the City’s 2016-2020 STWP
C18 | Expanded recreational facility: multi-use trails, 3 multi-purpose fields, 4 tennis courts, parking, restroom facility, landscaping |  |  |  | x | x | Community Development | TBD | General fund; Cobb County; Grant funds | Carried over from 2016 LCI Study
NATURAL & HISTORIC RESOURCES
NR1 | Seven Springs Walking Tour Markers; update and implement trail signage program. | x | x |  |  |  | Community Development; Economic Development | 70000 | General fund | Part of the City’s 2016-2020 STWP
NR2 | Phase II of park | x | x |  |  |  | Community Development; Public Works; SPLOST Program Manager | 976000 | 70% impact fees; 30% other including SPLOST funds | Part of the City’s 2016-2020 STWP
NR3 | Phase IV of Linear Park | x |  |  |  |  | Community Development; Public Works; SPLOST Program Manager | 488000 | 43% impact fees; 57% other, including SPLOST funds | Part of the City’s 2016-2020 STWP
NR4 | Impact fee program update for linear park | x |  |  |  |  | Community Development; Economic Development | Staff | - | Part of the City’s 2016-2020 STWP
NR5 | Maintenance of Landscaping on parkway/roads & at newly landscaped areas | x | x | x | x | x | Public Works | 10000 | General fund | Part of the City’s 2016-2020 STWP
NR6 | Develop tourism strategy centered around recreation and entertainment to include Bodiford House | x |  |  |  |  | Community Development; Economic Development; City Manager | TBD | TBD | Part of the City’s 2016-2020 STWP
NR7 | Investigate the potential for designating a local historic district and forming a historic preservation commission | x | x |  |  |  | Community Development | Staff | - | Part of the City’s 2016-2020 STWP
NH8 | Conduct a signage and wayfinding study that builds off the branding study from ED41 and creates a strategy to increase awareness of Powder Springs for Silver Comet Trail users, increase wayfinding capabilities throughout the City’s trail system, and create cohesive and attractive signage throughout the City. | x | x |  |  |  | Community Development | 40000 | General fund
NH9 | Implement the recommendations of the signage and wayfinding study |  |  | x | x | x | Community Development | TBD | TBD
TRANSPORTATION
TRAFFIC STUDIES
T1 | C.H. James Parkway & Brownsville Road |  | x |  |  |  | Public Works | 20000 | General fund; SPLOST | Project will include traffic study to retime traffic signal
T2 | C.H. James Parkway & Hill Road |  | x |  |  |  | Public Works | 20000 | General fund; SPLOST | Project will include traffic study to retime traffic signal
T3 | Richard D. Sailors Parkway & Old Lost Mountain Road |  | x |  |  |  | Public Works | 20000 | General fund; SPLOST | Project will include traffic study to retime traffic signal
T4 | Brownsville Road & Hiram-Lithia Springs Road |  | x |  |  |  | Public Works | 40000 | General fund; SPLOST | Project will include traffic study to retime traffic signal and install protected left signal phases
T5 | Powder Springs Road at Richard D. Sailors Parkway |  |  |  | x |  | Public Works | 15000 | General fund; SPLOST
T6 | Corridor study for Powder Springs Road | x |  |  |  |  | Public Works | 90000 | General fund; SPLOST | Study will examine a ~2 mile stretch of Powder Springs Road from Forest Hill Road to Anderson Farm Road. Partnership with City of Austell and Cobb County
T7 | Corridor study for Austell Powder Springs Road | x |  |  |  |  | Public Works | 40000 | General fund; SPLOST | Study will examine a ~1 mile stretch of Austell Powder Springs Road from Powder Springs Road to Clay Road. Partnership with City of Austell and Cobb County
ROADWAY
T8 | Murray Avenue A (Hotel Avenue to Atlanta Street): Remains one way, add 20’ angled parking on both sides |  |  | x | x | x | Community Development; Public Works | 245000 | General fund; SPLOST; LCI funding | Carried over from 2016 LCI Study
T9 | Murray Avenue B (Atlanta Street to Lewis Road): Add 18’, 90 degree parking on one side |  |  | x | x | x | Community Development; Public Works | 200000 | General fund; SPLOST; LCI funding | Carried over from 2016 LCI Study
T10 | Butner Street Extension: Add 20’ angled parking each side, add two 10’ travel lanes | x | x | x |  |  | Community Development; Public Works | 135000 | General fund; SPLOST; LCI funding | Carried over from 2016 LCI Study
T11 | Jackson Way Reconfiguration: two 10’ travel lanes | x | x | x |  |  | Community Development, Public Works | 120000 | General fund; SPLOST; LCI funding | Carried over from 2016 LCI Study
T12 | Hotel Avenue Extension: Add 20’ angled parking on both sides, add two 10’ travel lanes | x | x | x |  |  | Public Works, Private Developers | 235000 | General fund; SPLOST | Carried over from 2016 LCI Study
T13 | Florence Road at C.H. James Parkway |  |  |  | x |  | Public Works, GDOT | 60000 | General fund; SPLOST | Project will include adding a right turn lane to southbound Florence Road
T14 | Brownsville Road at Oglesby Road |  |  |  | x |  | Public Works | 200000 | General fund; SPLOST | Project will include adding a left turn lane to southbound Brownsville Road
T15 | New Macland Road at Publix and Home Depot |  |  |  | x |  | Public Works | 120000 | General fund; SPLOST | Project will include signalization of New Macland Road at Publix and Home Depot shopping centers
T16 | Brownsville Road at Kroger | x |  |  |  |  | Public Works | 120000 | General fund; SPLOST | Project will include signalization of Brownsville Road at Kroger shopping centers or addition of two way left turn lane to Brownsville Road
T17 | Widen New Macland Road |  | x |  |  |  | Public Works | 1800000 | General fund; SPLOST | Project will include addition of two way left turn lane to New Macland Road from Red Oak Drive to city limit
T18 | C.H. James striping and pavement marker improvements |  | x | x | x |  | GDOT | 40000 | State of Georgia | Project will include replacing reflective pavement markers along C H James Parkway
T19 | Curb cut off CH James Parkway at Hopeland Industrial to connect to Shipp Road |  | x | x | x |  | Public Works | TBD | TBD
T20 | Curb cut off CH James Parkway to connect to Oglesby Road with signalization | x | x | x |  |  | Public Works | TBD | TBD
T21 | Curb cut off CH James Parkway near Hill Road | x | x | x |  |  | Public Works | TBD | TBD
T22 | Realignment of Flint Road at Powder Springs Road | x | x | x |  |  | Public Works | TBD | TBD
T23 | Curb cut off CH James Parkway near Florence Road |  |  |  | x |  | Public Works | TBD | TBD
T24 | Curb cut off C.H. James Parkway at Paulding County line, with access road connecting to Sterlingbrooke Drive and traffic light |  | x |  |  |  | Public Works, GDOT | 570000 | General fund; SPLOST
T25 | New traffic signal at C.H. James Parkway at Sweetwater Avenue |  |  |  | x |  | Public Works, GDOT | 150000 | General fund; SPLOST
BICYCLE/PEDESTRIAN IMPROVEMENTS
T26a | 10' Concrete Multi-Use Trail Alternative A: Retrofit sidewalk on Lynn Drive from Old Lost Mountain Road to parking lot off Jackson Way to serve as connector from Silver Comet Trail off Old Lost Mountain Road to downtown. | x | x |  |  |  | Community Development, Public Works | TBD | SPLOST, LCI funding
T26b | 10' Concrete Multi-Use Trail Alternative B: From Silver Comet Trail Connector along Old Lost Mountain Road to Oakview Drive to Downtown/Lewis Road | x | x |  |  |  | Community Development, Public Works | TBD | SPLOST, LCI funding | Carried over from 2016 LCI Study
T27 | Recreation Trails: 12’ concrete trail from Brownsville Road south through floodplain | x | x | x | x |  | Community Development; Public Works | 3500000 | General fund, Cobb County, SPLOST, LCI funding, grant funding | Carried over from 2016 LCI Study
T28 | Designate a Trail Head at the intersection of Oakview Drive and Jackson Street at existing parking lot | x |  |  |  |  | Community Development; Public Works | TBD | General fund, Cobb County, SPLOST, LCI funding, grant funding
T29 | Austell Powder Springs Road Pedestrian Improvements |  | x |  |  |  | Community Development; Public Works | 3600000 | General fund; LCI funding | From Marietta Street to City limits
T30 | New Macland Road Pedestrian Improvements |  | x |  |  |  | Community Development; Public Works | 8500000 | General fund; LCI funding | From Marietta Street to City limits
T31 | Macedonia Road Pedestrian Improvements | x |  |  |  |  | Community Development; Public Works | 5200000 | General fund; LCI funding | From New Macland Road to Hopkins Road
T32 | Powder Springs Dallas Road Pedestrian Improvements |  |  | x |  |  | Community Development; Public Works | 1700000 | General fund; LCI funding | From Lucille Trail to Powder Springs Park and Ride Lot
T33 | Hill Road Pedestrian Improvements |  |  | x |  |  | Community Development; Public Works | 3250000 | General fund; LCI funding | From City limit to Brownsville Road
T34 | Carter Road Pedestrian Improvements |  |  |  | x |  | Community Development; Public Works | 800000 | General fund; LCI funding | From Powder Springs Road to Silver Comet Trail
T35 | Elliott Road Pedestrian Improvements |  |  |  |  | x | Community Development, Public Works | 1300000 | General fund; LCI funding; Cobb County | From Silverbrooke Crossing to Silver Comet Trail; joint project with County
T36 | Powder Springs Creek Trail |  |  | x |  |  | Community Development; Public Works | 2200000 | General fund; LCI funding | From Powder Springs Dallas Road and Lucille Trail to Hill Road through Powder Springs Creek flood plain
T37 | Lewis Road Landscape: median landscaping along whole corridor, inside median and at back of sidewalk |  | x | x | x |  | Community Development; Public Works | TBD | TBD | Carried over from 2016 LCI Study
T38 | Butner Street Streetscape: landscaped planters, sidewalks |  | x | x | x |  | Community Development; Public Works | 35000 | TBD | Carried over from 2016 LCI Study
T39 | Jackson Way Streetscape: reconfiguration, landscaped planters, sidewalks, both sides |  | x | x | x |  | Community Development; Public Works | 245000 | General fund, SPLOST, LCI funding, grand funding | Carried over from 2016 LCI Study
T40 | Hotel Avenue Streetscape: landscaping, sidewalks from Murray Avenue to Butner Street |  | x | x | x |  | Community Development; Public Works | 110000 | General fund, SPLOST, LCI funding, grand funding | Carried over from 2016 LCI Study
T41 | Dillard Street Sharrow Markings: from Pineview Drive south to Atlanta Street |  | x | x | x |  | Community Development; Public Works | 12500 | TBD | Carried over from 2016 LCI Study
T42 | Atlanta Street Sharrow Markings: from Dillard Street to Old Austell Road |  |  | x | x |  | Community Development; Public Works | 12500 | TBD | Carried over from 2016 LCI Study
T43 | Marietta Street Sharrow Markings: from Dillard Street to Old Lost Mountain Road and Powder Springs Dallas Road intersection |  | x | x | x |  | Community Development; Public Works | 18500 | TBD | Carried over from 2016 LCI Study
T44 | Powder Springs/Dallas Road Sharrow Markings: from Old Lost Mountain Road to Lucille Creek Trail entrance |  |  | x | x |  | Community Development; Public Works | 16500 | TBD | Carried over from 2016 LCI Study
T45 | Grady Grier Drive Sharrow Markings: to Old Austell Road |  |  |  | x |  | Community Development; Public Works | 17500 | TDB | Carried over from 2016 LCI Study
T46 | Hopkins Road Sharrows |  |  |  | x |  | Community Development; Public Works | 25000 | General fund | From Powder Springs Road to City Limits
T47 | Brownsville Road Sharrows |  |  |  | x |  | Community Development; Public Works | 20000 | General fund | From C.H. James Parkway to Marietta Street
TRANSIT
T48 | MARTA connection bus |  | x |  |  |  | Public Works; MARTA; CobbLink | TBD | TBD | Project will include buss line connecting from Powder Springs Park & Ride Lot to Hamilton E. Holmes MARTA Station
T49 | Flex Bus expansion | x |  |  |  |  | Public Works; CobbLink | TBD | TBD | Project will include expanding Flex Zone 1 service to the Powder Springs City Limits
TOTAL | [7 empty] | 47751000

## Sheet2
T42 | Curb cut off C.H. James Parkway with access road to Oglesby Road with new traffic signals | x | x |  |  |  | Public Works | TBD | TBD
T43 | Curb cut off C.H. James Parkway near Hill Road |  | x | x |  |  | Public Works | TBD | TBD
T44 | Realignment of Flint Road at Powder Springs Road |  |  |  |  | x | Public Works | TBD | TBD | 550000 in Cobb 2016 SPLOST
T45 | Curb cut off C.H. James Parkway near Florence Road with access road |  |  | x | x |  | Public Works | TBD | TBD
T46 | Curb cut off C.H. James Parkway at Paulding County line, with access road connecting to Sterlingbrooke Drive and traffic light |  |  |  |  | x | Public Works | TBD | TBD
T47 | New traffic signal at C.H. James Parkway at Sweetwater Avenue |  | x |  |  |  | Public Works | TBD | TBD
T48 | New traffic signal at C.H. James Parkway at Sterlingbrooke Drive |  |  |  |  | x | Public Works | TBD | TBD
T6 | Corridor study for Powder Springs Road | [5 empty] | Public Works
T7 | Corridor study for Austell Powder Springs Road | [5 empty] | Public Works