## Sheet2
City of Powder Springs DRAFT 2022-2026 Short Term Work Plan
# | Project | 2022 | 2023 | 2024 | 2025 | 2026 | Responsible Party | Estimated Cost | Funding Source | Notes
ECONOMIC DEVELOPMENT
ED1 | Host annual downtown business open house; Host annual reception for downtown property owners. | x | x | x | x | x | Economic Development | TBD | General fund | Part of the City's 2021-2025 STWP
ED2 | Public outreach: messenger; signage; brochures and cards, and website review to be conducted bi-monthly | x | x | x | x | x | City Manager; Economic Development; DAPS; DDA | Staff | N/A | Part of the City's 2021-2025 STWP
ED3 | Work through DDA to solicit proposals consistent with LCI recommendations | x |  |  |  |  | City Manager; Economic Development; City Clerk | 25000 | General fund | Part of the City's 2021-2025 STWP
ED4 | Develop and continue to refine properties around Thurman Springs Park | x | x | x | x | x | Community Development; SPLOST Program Manager; Economic Development | 26500 | General fund | Part of the City's 2021-2025 STWP
ED5 | Develop Economic Development Strategy – update annually, including evaluation of marketing to hits on city and economic development websites | x | x | x | x | x | Economic Development; Community Development | 30000 | General fund | Part of the City's 2021-2025 STWP
ED6 | Host annual meetings with local businesses, including those within industries recommended for recruitment in Fanning Report | x | x | x | x | x | City Manager; Economic Development; DAPS; DDA | TBD | General fund | Part of the City's 2021-2025 STWP
ED7 | Identify and attend industry events occurring within the region | x | x | x | x | x | City Manager; Economic Development; DAPS | Staff | N/A | Part of the City's 2021-2025 STWP
ED8 | Inventory and assess all potential and existing industrial and commercial properties | x | x | x | x | x | City Manager; Economic Development; DAPS | Staff | N/A | Part of the City's 2021-2025 STWP
ED9 | Create printed and electronic site information packets on potential development areas, vacant sites, and downtown properties. Create brochures for targeted industries. | x | x | x | x | x | Economic Development | TBD | General fund | Part of the City's 2021-2025 STWP
ED10 | Recruit developer for mixed use remodel of existing town square | x |  |  |  |  | Economic Development; DDA | TBD | General fund | Part of the City's 2021-2025 STWP
ED11 | Market the economic development office as the “go-to” for local business owners in solving problems | x | x | x | x | x | Economic Development | Staff | N/A | Part of the City's 2021-2025 STWP
ED12 | Further develop the local business ambassador program | x | x | x |  |  | Economic Development | Staff | N/A | Part of the City's 2021-2025 STWP
ED13 | Develop and update an online business directory in partnership with the Powder Springs Business Group | x | x | x |  |  | Economic Development | TBD | General fund | Part of the City's 2021-2025 STWP
ED14 | Host business tours for community leaders | x | x | x | x | x | Economic Development; Consultants | TBD | General fund | Part of the City's 2021-2025 STWP
ED15 | Host a tour of available properties with regional developers | x |  |  |  |  | Economic Development | TBD | General fund | Part of the City's 2021-2025 STWP
ED16 | Host a Developers Day |  | x |  | x |  | Economic Development | TBD | General fund | Part of the City's 2021-2025 STWP
ED17 | Create an internship program | x |  |  |  |  | Economic Development | Staff | N/A | Part of the City's 2021-2025 STWP
ED18 | Create a video on "Why Powder Springs?" | x |  |  |  |  | Economic Development | TBD | TBD | Part of the City's 2021-2025 STWP
ED19 | Explore resources available through Kennesaw State University | x | x | x | x | x | Economic Development | Staff | N/A | Part of the City's 2021-2025 STWP
ED20 | Convene real estate brokers and property owners for commercial and industrial properties | x | x | x | x | x | Economic Development | Staff | N/A | Part of the City's 2021-2025 STWP
ED21 | Gather intelligence on “market holes” in Powder Springs | x |  |  |  |  | Economic Development; Consultants | TBD | TBD | Part of the City's 2021-2025 STWP
ED22 | Explore the feasibility of developing a co-working space; consider alternative solutions in light of COVID-19 | x |  |  |  |  | Economic Development; Consultants | TBD | TBD | Part of the City's 2021-2025 STWP
ED23 | Develop a tutorial on how to do business in Powder Springs | x |  |  |  |  | Economic Development; Community Development | Staff | N/A | Part of the City's 2021-2025 STWP
ED24 | Investigate the potential for a National Main Street and Georgia Main Street Designation |  | x |  |  |  | Economic Development; Community Development | Staff | N/A | Part of the City's 2021-2025 STWP
ED25 | Conduct a marketing study that will research Powder Springs' target demographic(s), and create strategies for attracting new residents, business owners, tourists, and development. | x |  |  |  |  | Economic Development; Community Development | 40000 | General fund | Part of the City's 2021-2025 STWP
ED26 | DCA Broadband Ready Community Designation |  | x |  |  |  | Economic Development; Community Development | Staff | N/A | Adopt DCA's model ordinance
LAND USE
LU1 | Annex parcels identified in the comprehensive plan | x | x | x | x | x | All Departments | Staff | N/A | Part of the City's 2021-2025 STWP
LU2 | Update City boundary map with actions through the General Assembly - annual submittals as appropriates | x | x | x | x | x | Community Development | Staff | N/A | Part of the City's 2021-2025 STWP
LU3 | Update the Unified Development Code to eliminate discrepancies, make it more user friendly, and review and revise regulations | x | x | x | x | x | Community Development | Staff | N/A | Part of the City's 2021-2025 STWP
LU4 | Major comprehensive plan update |  |  |  |  | x | Community Development; Consultants | 150000 | General fund
LU5 | Downtown Design Guidelines | x |  |  |  |  | Community Development; Consultants | 25000 | General fund
LU6 | LCI Supplement Study: plans for redevelopment areas |  |  | x | x |  | Community Development; Consultants; ARC | 30000 | General fund; ARC | Estimated cost reflects City's required 20% match
COMMUNITY FACILITIES & SERVICES
C1 | Community Rating System to lower flood insurance premiums | x | x | x | x | x | Administration; Community Development | 5000 | General fund | Part of the City's 2021-2025 STWP
C2 | Facilitate functions and events at Thurman Springs Park | x | x | x | x | x | Community Development; Parks & Recreation | 80000 | General fund | Part of the City's 2021-2025 STWP
C3 | Construct parking garage downtown | x | x | x | x |  | Community Development; Public Works; SPLOST Program Manager; Economic Development, DDA | 3600000 | SPLOST/TBD | Part of the City's 2021-2025 STWP
C4 | Infrastructure reporting implementation | x | x | x | x | x | Community Development; Public Works | TBD | General fund | Part of the City's 2021-2025 STWP
C5 | Lancer Sidewalks Phase II |  | x |  |  |  | Public Works | TBD | SPLOST/General fund | Part of the City's 2021-2025 STWP
C6 | Theatre and reception hall: market for events, schedule events, and maintenance | x | x | x | x | x | City Manager; Community Development; Parks & Recreation | TBD | General fund | Part of the City's 2021-2025 STWP
C7 | Annual citizen survey | x | x | x | x | x | City Manager; City Clerk | Staff | N/A | Part of the City's 2021-2025 STWP
C8 | Develop marketing and use strategy for city trails (5K; PD Bike Patrol; Cameras; etc.) | x | x | x | x | x | Community Development; Police Department; Economic Development; City Manager; Parks & Recreation | 40000 | General fund | Part of the City's 2021-2025 STWP
C9 | Institute Community Policing Program to include CAP, Bridge Gap meetings, Business Watch, etc | x | x | x | x | x | Police Department; Parks & Recreation | Staff | N/A | Part of the City's 2021-2025 STWP
C10 | Institute Community Emergency Response Team program; update COOP | x | x | x | x | x | Finance; Police Department; Public Works; City Manager | Staff | N/A | Part of the City's 2021-2025 STWP
C11 | Continue to implement monthly playground safety inspection program | x | x | x | x | x | Parks & Recreation | 2000 | General fund | Part of the City's 2021-2025 STWP
C12 | Develop and implement SOP's for the Downtown Park | x | x | x | x | x | Parks & Recreation | Staff | N/A | Part of the City's 2021-2025 STWP
C13 | New Civic Center Building Programming |  | x |  |  |  | City Manager; Community Development; Finance | TBD | TBD | Programming and design study by architects/consultants
NATURAL & HISTORIC RESOURCES
NH1 | Seven Springs Walking Tour Markers |  | x |  |  |  | Community Development; Economic Development; Parks & Recreation | 70000 | General fund | Part of the City's 2021-2025 STWP
NH2 | Complete Linear Park |  | x |  |  |  | Community Development; Public Works; SPLOST Program Manager; Parks & Recreation | 1464000 | Impact fees; SPLOST | Part of the City's 2021-2025 STWP
NH3 | Maintenance of landscaping on parkway/roads & at newly landscaped areas | x | x | x | x | x | Public Works; Parks & Recreation | 50000 | General fund | Part of the City's 2021-2025 STWP; $10,000 annual budget
NH4 | Bike Friendly Certification | x | x | x | x | x | Community Development; Parks & Recreation | Staff | N/A | Part of the City's 2021-2025 STWP
NH5 | Implement the recommendations of the signage and wayfinding study | x | x | x | x |  | Community Development; Parks & Recreation | TBD | TBD | Part of the City's 2021-2025 STWP
NH6 | Conduct a parks, recreation, and greenspace master plan |  |  | x |  |  | Community Development; Parks & Recreation | 75000 | General fund | Part of the City's 2021-2025 STWP
TRANSPORTATION
ADDITIONAL STUDIES
T1 | C.H. James Parkway & Brownsville Road Traffic Study |  | x |  |  |  | Public Works | 20000 | General Fund/SPLOST | Part of the City's 2021-2025 STWP; Project will include traffic study to retime traffic signal
T2 | C.H. James Parkway & Hill Road Traffic Study |  | x |  |  |  | Public Works | 20000 | General Fund/SPLOST | Part of the City's 2021-2025 STWP; Project will include traffic study to retime traffic signal
T3 | Richard D. Sailors Parkway & Old Lost Mountain Road Traffic Study |  | x |  |  |  | Public Works | 20000 | General Fund/SPLOST | Part of the City's 2021-2025 STWP; Project will include traffic study to retime traffic signal
T4 | Brownsville Road & Hiram-Lithia Springs Road Traffic Study |  | x |  |  |  | Public Works | 40000 | General Fund/SPLOST | Part of the City's 2021-2025 STWP; Project will include traffic study to retime traffic signal and install protected left signal phases
T5 | C.H. James Parkway at Richard D. Sailors Parkway Traffic Study |  | x |  |  |  | Public Works | 15000 | General Fund/SPLOST | Part of the City's 2021-2025 STWP; Project will include traffic study to evaluate operational improvements at the intersection. Interim improvements could include striping of northbound Powder Springs Road to better delineate lanes
T6 | Brownsville Road at Linked UP Church Parking Lot Intersection Study |  | x |  |  |  | Public Works | TBD | TBD
T7 | Analyze Ways to Allow Increased Connectivity along C.H. James Parkway | x | x | x |  |  | Public Works | TBD | TBD
ROADWAY
T8 | Butner Street Extension: Add 20' angled parking on each side, add two 10' travel lanes |  | x |  |  |  | Community Development; Public Works | 135000 | General Fund/SPLOST/LCI Funding | Part of the City's 2021-2025 STWP
T9 | Florence Road at C.H. James Parkway |  | x |  |  |  | Public Works; GDOT | 60000 | General Fund/SPLOST | Part of the City's 2021-2025 STWP; Project will include adding a right turn lane to southbound Florence Road
T10 | Brownsville Road at Oglesby Road |  | x |  |  |  | Public Works | 200000 | General Fund/SPLOST | Part of the City's 2021-2025 STWP; Project will include adding a left turn lane to southbound Brownsville Road
T11 | New MacLand Road at Publix and Home Depot |  | x |  |  |  | Public Works | 120000 | General Fund/SPLOST | Part of the City's 2021-2025 STWP; Project will include signalization of New Macland Road at Publix and Home Depot shopping centers
T12 | Brownsville Road at Kroger |  |  | x |  |  | Public Works | 120000 | General Fund/SPLOST | Part of the City's 2021-2025 STWP; Project will include signalization of Brownsville Road at Kroger shopping centers or addition of two way left turn lane to Brownsville Road
T13 | C.H. James Parkway at Powder Springs-Dallas Road Intersection Improvements |  |  | x |  |  | Public Works | TBD | General Fund/SPLOST | Add right-hand turn lanes
T14 | C.H. James Parkway Striping and Pavement Marker Improvements |  | x |  |  |  | GDOT | 40000 | GDOT | Part of the City's 2021-2025 STWP; Project will include replacing reflective pavement markers along C H James Parkway
T15 | Curb Cut Off C.H. James Parkway at Hopeland Industrial to Connect to Shipp Road |  | x |  |  |  | Public Works | TBD | TBD | Part of the City's 2021-2025 STWP
T16 | Curb Cut and Access Road Off C.H. James Parkway to Connect to Oglesby Road |  | x |  |  |  | Public Works | TBD | TBD | Part of the City's 2021-2025 STWP; Intersection control type TBD
T17 | Curb Cut Off C.H. James Parkway near Hill Road |  | x |  |  |  | Public Works | TBD | TBD | Part of the City's 2021-2025 STWP
T18 | Curb Cut Off C.H. James Parkway near Florence Road |  |  | x |  |  | Public Works, GDOT | TBD | TBD | Part of the City's 2021-2025 STWP
T19 | Curb Cut Off C.H. James Parkway at Paulding County line, with access road connecting to Sterlingbrooke Drive and Traffic Light |  | x |  |  |  | Public Works, GDOT | 570000 | General Fund/SPLOST | Part of the City's 2021-2025 STWP
T20 | New Traffic Signal at C.H. James Parkway at Sweetwater Avenue |  |  | x |  |  | Public Works, GDOT | 150000 | General Fund/SPLOST | Part of the City's 2021-2025 STWP
T21 | New Traffic Signal at C.H. James Parkway at Sterlingbrooke Drive |  |  | x |  |  | Public Works, GDOT | TBD | TBD
T22 | Signals (Citywide) | x |  |  |  |  | Public Works | 750000 | SPLOST | From Cobb County SPLOST Project List
T23 | Street Resurfacing (Citywide) | x |  |  |  |  | Public Works | 3600000 | SPLOST | From Cobb County SPLOST Project List
T24 | Sidewalk & Drainage Associated with Road Projects | x |  |  |  |  | Public Works | 1000000 | SPLOST | From Cobb County SPLOST Project List
T25 | New Traffic Signal at Powder Springs Road at Creekwood by Paran Homes and Powder Springs Storage |  |  | x |  |  | Public Works | TBD | TBD
T26 | New Parallel Access Road from Shopping Area east of Powder Springs Road SW at Richard D Sailors Parkway to New Intersection at Powder Springs Road at Creekwood by Paran Homes and Powder Springs Storage |  |  | x |  |  | Public Works | TBD | TBD
BICYCLE/PEDESTRIAN
T27 | 10' to 12' Concrete Multi-Use Trail Phase 2: From Silver Comet Trail Connector along Old Lost Mountain Road to Oakview Drive to Downtown/Lewis Road |  |  | x |  |  | Community Development; Public Works; Parks & Recreation | TBD | SPLOST/LCI Funding | Part of the City's 2021-2025 STWP
T28 | Austell Powder Springs Road to Silver Comet Trail Connection Option 1: From Jackson Way at Pineview Drive along Pineview Drive and Marietta Street to Austell Powder Springs Road SW at Marietta Street |  |  | x |  |  | Community Development; Public Works; Parks & Recreation | TBD | TBD | Alternative to T29
T29 | Austell Powder Springs Road to Silver Comet Trail Connection Option 2: From Austell Powder Springs Road SW at Marietta Street along Marietta Street and Lindley Road to Silver Comet Trail Connection |  |  | x |  |  | Community Development; Public Works; Parks & Recreation | TBD | TBD | Alternative to T28
T30 | Recreation Trails: 12' Concrete Trail from Brownsville Road South through Floodplain |  |  | x |  |  | Community Development; Public Works; Parks & Recreation | 3500000 | General Fund/Cobb County/SPLOST/ LCI Funding/Grant Funding | Part of 2016 LCI Study
T31 | Pineview Drive Pedestrian and Roadway Improvements |  |  | x |  |  | Community Development; Public Works | TBD | TBD | Pineview Drive to be westbound one-way from Silver Comet Trail to Jackson Way and 10' Concrete Multi-Use Trail along Pineview Drive to Jackson Way
T32 | Austell Powder Springs Road Pedestrian Improvements (from Marietta Street to city limits) |  |  | x |  |  | Community Development; Public Works | 3600000 | General Fund/LCI Funding | Part of the City's 2021-2025 STWP
T33 | New Macland Road Pedestrian Improvements (from Marietta Street to city limits) |  |  | x |  |  | Community Development; Public Works | 8500000 | General Fund/LCI Funding | Part of the City's 2021-2025 STWP
T34 | Macedonia Road Pedestrian Improvements (from New Macland Road to Hopkins Road) |  |  | x |  |  | Community Development; Public Works | 5200000 | General Fund/LCI Funding | Part of the City's 2021-2025 STWP
T35 | Powder Springs Dallas Road Pedestrian Improvements (from Lucille Trail to Powder Springs Park and Ride Lot) |  |  | x |  |  | Community Development; Public Works | 1700000 | General Fund/LCI Funding | Part of the City's 2021-2025 STWP
T36 | Hill Road Pedestrian Improvements (from city limits to Brownsville Road) |  |  | x |  |  | Community Development; Public Works | 3250000 | General Fund/LCI Funding | Part of the City's 2021-2025 STWP
T37 | Carter Road Pedestrian Improvements (from Powder Springs Road to Silver Comet Trail) |  |  | x |  |  | Community Development; Public Works | 800000 | General Fund/LCI Funding | Part of the City's 2021-2025 STWP
T38 | Elliott Road Pedestrian Improvements (from Silverbrook Crossing to Silver Comet Trail) |  |  | x |  |  | Community Development; Public Works | 1300000 | General Fund/LCI Funding/Cobb County | Part of the City's 2021-2025 STWP
T39 | Powder Springs Creek Trail (from Powder Springs Dallas Road and Lucille Trail to Hill Road through Powder Springs Creek floodplain) |  |  | x |  |  | Community Development; Public Works; Parks & Recreation | 2200000 | General Fund/LCI Funding | Part of the City's 2021-2025 STWP
T40 | Lewis Road Landscaping: median landscaping along corridor, inside median and at back of sidewalk |  |  | x |  |  | Community Development; Public Works; Parks & Recreation | TBD | TBD | Part of the City's 2021-2025 STWP
T41 | Butner Street Streetscape: landscaped planters and sidewalks |  |  | x |  |  | Community Development; Public Works; Parks & Recreation | 35000 | TBD | Part of the City's 2021-2025 STWP
T42 | Jackson Way Streetscape: reconfiguration, landscaped planters, and sidewalks on both sides |  |  | x |  |  | Community Development; Public Works; Parks & Recreation | 245000 | General Fund/SPLOST/LCI Funding/Grand Funding | Part of the City's 2021-2025 STWP
T43 | Hotel Avenue Landscape |  |  | x |  |  | Community Development; Public Works; Parks & Recreation | 110000 | General Fund/SPLOST/LCI Funding/Grand Funding | Part of the City's 2021-2025 STWP
T44 | Dillard Street Sharrow Markings (from Pineview Drive South to Atlanta Street) |  |  | x |  |  | Community Development; Public Works | 12500 | TBD | Part of the City's 2021-2025 STWP
T45 | Atlanta Street Sharrow Markings (from Dillard Street to Old Austell Road) |  |  | x |  |  | Community Development; Public Works | 12500 | TBD | Part of the City's 2021-2025 STWP
T46 | Marietta Street Sharrow Markings (from Dillard Street to Old Lost Mountain Road and Powder Springs Dallas Road intersection) |  |  | x |  |  | Community Development; Public Works | 18500 | TBD | Part of the City's 2021-2025 STWP
T47 | Powder Springs Dallas Road Sharrow Markings (from Old Lost Mountain Road to Lucille Creek Trail entrance) |  |  | x |  |  | Community Development; Public Works | 16500 | TBD | Part of the City's 2021-2025 STWP
T48 | Grady Grier Drive Sharrow Markings (from Old Austell Road to end of road) |  |  | x |  |  | Community Development; Public Works | 17500 | TBD | Part of the City's 2021-2025 STWP
T49 | Hopkins Road Sharrows (from Powder Springs Road to city limits) |  |  | x |  |  | Community Development; Public Works | 25000 | General Fund | From Powder Springs Road to City Limits
T50 | Brownsville Road Sharrows (from C.H. James Parkway to Marietta Street) |  |  | x |  |  | Community Development; Public Works | 20000 | General Fund | From C H James Parkway to Marietta Street
TRANSIT
T51 | MARTA Connection Bus |  |  | x |  |  | Public Works; MARTA; CobbLink | TBD | TBD | Part of the City's 2021-2025 STWP; Project will include bus line connecting from Powder Springs Park & Ride Lot to Hamilton E. Holmes MARTA Station
T52 | Flex Bus Expansion |  |  | x |  |  | Public Works; CobbLink | TBD | TBD | Part of the City's 2021-2025 STWP; Project will include expanding Flex Zone 1 service to the Powder Springs city limits
Designates new project