## Sheet1
2022 Short Term Work Plan - Report of Accomplishments
# | Project | Completed | Underway | Postponed | Dropped | Notes
ECONOMIC DEVELOPMENT
ED1 | Host annual downtown business open house; Host annual reception for downtown property owners. |  |  | X |  | Budgetary Restrictions/ COVID Restrictions
ED2 | Public outreach: messenger; signage; brochures and cards, and website review to be conducted bi-monthly |  | X
ED3 | Work through DDA to solicit proposals consistent with LCI recommendations |  | X
ED4 | Develop and continue to refine properties around Thurman Springs Park |  | X
ED5 | Develop Economic Development Strategy – update annually, including evaluation of marketing to hits on city and economic development websites |  | x
ED6 | Host annual meetings with local businesses, including those within industries recommended for recruitment in Fanning Report |  |  | x |  | Budgetary Restrictions/ COVID Restrictions
ED7 | Identify and attend industry events occurring within the region | x
ED8 | Inventory and assess all potential and existing industrial and commercial properties |  | x
ED9 | Create printed and electronic site information packets on potential development areas, vacant sites, and downtown properties. Create brochures for targeted industries. |  | x
ED10 | Recruit developer for mixed use remodel of existing town square | x
ED11 | Market the economic development office as the “go-to” for local business owners in solving problems |  | x
ED12 | Further develop the local business ambassador program | x
ED13 | Develop and update an online business directory in partnership with the Powder Springs Business Group |  | x
ED14 | Host business tours for community leaders | x
ED15 | Host a tour of available properties with regional developers | x
ED16 | Host a Developers Day | x
ED17 | Create an internship program |  |  | x |  | Budgetary Restrictions/ COVID Restrictions
ED18 | Create a video on "Why Powder Springs?" |  | x
ED19 | Explore resources available through Kennesaw State University | x
ED20 | Convene real estate brokers and property owners for commercial and industrial properties |  | x
ED21 | Gather intelligence on “market holes” in Powder Springs | x
ED22 | Explore the feasibility of developing a co-working space; consider alternative solutions in light of COVID-19 |  | x
ED23 | Develop a tutorial on how to do business in Powder Springs |  | x
ED25 | Conduct a marketing study that will research Powder Springs' target demographic(s), and create strategies for attracting new residents, business owners, tourists, and development. |  | x
LAND USE
LU1 | Annex parcels identified in the comprehensive plan |  | x |  |  | Process began in January of 2022, but decided to postpone to allow more citizen outreach.
LU2 | Update City boundary map with actions through the General Assembly - annual submittals as appropriates |  | x
LU3 | Update the Unified Development Code to eliminate discrepancies, make it more user friendly, and review and revise regulations | x |  |  |  | Ongoing
LU5 | Downtown Design Guidelines |  |  | x |  | Budgetary/Staffing
COMMUNITY FACILITIES & SERVICES
C1 | Community Rating System to lower flood insurance premiums | x |  |  |  | Ongoing
C2 | Facilitate functions and events at Thurman Springs Park | x |  |  |  | Ongoing
C3 | Construct parking garage downtown |  | x
C4 | Infrastructure reporting implementation |  | x
C6 | Theatre and reception hall: market for events, schedule events, and maintenance |  |  | x |  | Construction of City Hall required relocation of city space to include the theater and reception
C7 | Annual citizen survey |  | x |  |  | The City is evaluating a different survey tool. The City conducted a City wide survey in the Fall of 2021. The City expects to conduct another City wide survey by year’s end. The City conducted a skatepark survey – open to the public – in the 2nd quarter of 2022.
C8 | Develop marketing and use strategy for city trails (5K; PD Bike Patrol; Cameras; etc.) | x |  |  |  | Established and certfied trails have been established and have been utilized by organizations wanting to hold 5k races.
C9 | Institute Community Policing Program to include CAP, Bridge Gap meetings, Business Watch, etc |  |  | x |  | Seeking a part time employee or consultant
C10 | Institute Community Emergency Response Team program; update COOP |  |  | x |  | Seeking a part time employee or consultant
C11 | Continue to implement monthly playground safety inspection program | x |  |  |  | Conducted by Cobb and Powder Springs Parks
C12 | Develop and implement SOP's for the Downtown Park |  | x |  |  | These were written and are currently being reviewed for updates
| Parking improvements on Murray Avenue and Jackson Way | x
| Completion of pavillion at Powder Springs Park | x
| Complete Linear Park |  | x |  |  | Skate park designed and planned.
| Tasers and mobile and body cameras | x
NATURAL & HISTORIC RESOURCES
NH3 | Maintenance of landscaping on parkway/roads & at newly landscaped areas | x |  |  |  | Ongoing
NH4 | Bike Friendly Certification |  | x
NH5 | Implement the recommendations of the signage and wayfinding study |  | x
TRANSPORTATION
ADDITIONAL STUDIES
T7 | Analyze Ways to Allow Increased Connectivity along C.H. James Parkway |  | x
T9 | Florence Road at C.H. James Parkway | x
ROADWAY
T22 | Signals (Citywide) |  | x
T23 | Street Resurfacing (Citywide) | x |  |  |  | Ongoing
T24 | Sidewalk & Drainage Associated with Road Projects |  |  | x
| CH James Pkwy at RDS - intersection improvements | x
| Brownsville Road Project |  | x